Prairie Telehealth Network (PTN) - BA Portfolio Project

Fictional case study

Phase 1 of 7: Project Brief

Prepared By: Dwij Siyal

Date Created: 04-July-2026

Version 1.0

TABLE OF CONTENTS

Background	2

Business Problem	2

Project Objective	2

Scope	3

In scope	3

Out of scope	3

Assumptions	3

Constraints	3

Success Criteria	3

High-Level Stakeholders	4

Project Phases	4

# Project Brief:

# Vendor Data Onboarding & Integration Process

# Background

PTN is a fictional provincial health authority that coordinates virtual care services across urban and rural communities, including virtual visits, telehealth consultations, and remote patient monitoring (RPM). To scale these services, PTN contracts with third-party technology vendors who provide the platforms and devices patients and clinicians use.

Each vendor delivers usage and clinical data back to PTN in a format that is internally standardized for their own platform but no standardized summary layer exists across vendors. There is no shared data dictionary defining how vendor-specific fields should roll up into a common set of program metrics.

# Business Problem

The PTN Analytics & Reporting team manually reconciles vendor files each month to produce program performance reports (utilization, patient outcomes, SLA compliance) for provincial health ministry stakeholders. Because each vendor's detailed data is structured differently, the same monthly Ministry metrics must be manually re-derived from three structurally different datasets each cycle. Separately, no consistent structure exists for turning vendor detail data into service-specific operational dashboards used internally by program teams.

This manual, ad hoc process is:

- Slow: approximately 6-8 business days per reporting cycle spent on cleanup and reconciliation rather than analysis

- Error-prone: mismatched field definitions (e.g., one vendor's "session_duration" is recorded in minutes, another's in seconds) have caused reporting inaccuracies

- Not scalable: PTN plans to onboard 2-3 new telehealth vendors within the next 12 months, and the current process cannot absorb that growth without adding headcount

# Project Objective

Design and document a standardized vendor data onboarding process for PTN, including:

- A standardized monthly summary schema, extracted from each vendor's detailed data, for consistent reporting to the Ministry of Health and other external stakeholders

- A defined approach for using each vendor's detailed data to support service-specific operational dashboards (Virtual Visits, Telehealth, RPM)

- A repeatable data mapping methodology so future vendors can be onboarded with minimal manual rework

# Scope

## In scope

- Current state process mapping (how vendor data is received and reconciled today)

- Stakeholder analysis for the onboarding process

- Business, functional, and non-functional requirements for the summary extraction process and dashboard data usage

- Data mapping table for 3 representative fictional vendors: detailed vendor fields → standardized summary schema

- Conceptual definition of service-level dashboard data needs (not dashboard build)

- Future state process map reflecting the recommended process

## Out of scope

- Actual system/ETL build or dashboard development (this is a business analysis deliverable, not a technical implementation)

- Vendor contract or legal terms

- Real-time data integration (initial scope is batch/periodic file submission)

# Assumptions

- Vendors submit detailed data via secure file transfer (e.g., SFTP) on a monthly cadence

- PTN has an existing data warehouse/reporting layer that would consume both the summary and detail schemas

- Vendors have sufficient technical capability to export data against a documented specification

# Constraints

- No additional budget for new tooling in year one. The solution should work within PTN's existing reporting infrastructure

- Vendors vary in technical maturity; the summary extraction specification must be usable by less sophisticated vendors, not just enterprise-grade ones

# Success Criteria

- Reduce manual reconciliation effort from ~6-8 days to ~2 days per reporting cycle

- Zero data mapping errors caused by undocumented field definitions

- New vendor onboarding time reduced from ~4-6 weeks to ~2 weeks

# High-Level Stakeholders

Full stakeholder matrix and RACI chart are developed in Phase 3.

| Role | Interest in this project |
| --- | --- |
| Director, Virtual Care Programs | Project sponsor; accountable for program reporting accuracy to the Ministry |
| Analytics & Reporting Team Lead | Owns the monthly reconciliation process this project aims to fix |
| Vendor Relationship Manager | Manages vendor communication and onboarding timelines |
| IT / Data Integration Lead | Will implement the summary extraction logic and dashboard data feeds |
| Vendor Technical Contacts (x3) | Provide detailed-format data; must adopt the summary specification |
| Ministry of Health Reporting Liaison | Primary consumer of the standardized monthly summary reports |

# Project Phases

- 1. Project Brief (this document)

- 2. Current State Process Map

- 3. Stakeholder Analysis (Matrix + RACI)

- 4. Requirements Document (Business, Functional, Non-Functional)

- 5. Data Mapping Table (3 vendors → standardized summary schema)

- 6. Future State Process Map

- 7. Final Portfolio Package