## RACI Chart
Prairie Telehealth Network (PTN) — BA Portfolio Project
Fictional case study
Phase 3 of 7: RACI chart
Prepared by Dwij Siyal
Date Created: 04-July-2026
Version 1.0
RACI Chart
Roles and accountability across the vendor onboarding process
Activity | Business Analyst | Director (Sponsor) | Analytics & Reporting Lead | IT / Data Integration Lead | Vendor Relationship Mgr | Program / Service Leads | Vendor Technical Contacts | Ministry Liaison
Define business & functional requirements | R | A | C | C | C | C | I | I
Design standardized summary schema | R | I | A | C | I | I | I | C
Define dashboard data requirements (detail schema usage) | R | I | C | C | I | A | I | I
Build vendor-to-summary data mapping specification | R | I | A | C | C | I | C | I
Design future state onboarding process & intake spec | R | A | C | C | C | I | I | I
Adjust vendor export format to match specification | C | I | I | C | A | I | R | I
Build summary extraction & dashboard data feeds (technical) | C | I | C | R/A | I | C | I | I
Generate & QA monthly summary report | C | I | R/A | I | I | I | I | I
Submit monthly report to Ministry of Health | I | A | R | I | I | I | I | I
Approve / sign off final deliverables | R | A | C | C | C | C | I | I
RACI Legend
R | R: Responsible — Does the work
A | R: Accountable — Owns the outcome; final approval
C | R: Consulted — Provides input before/during the work
I | R: Informed — Kept updated on progress or outcome