## Stakeholder Matrix
Prairie Telehealth Network (PTN) — BA Portfolio Project
Fictional case study
Phase 3 of 7: Stakeholder Analysis
Prepared by Dwij Siyal
Date Created: 04-July-2026
Version 1.0
Stakeholder Matrix
Power / Interest grid (who to engage, and how)
Stakeholder | Group | Power | Interest | Quadrant | Engagement Strategy | Key Concern
Director, Virtual Care Programs | Sponsor | High | High | Manage Closely | Involve in key milestone reviews; escalation point for scope/priority decisions | Ministry accountability and program reputation if reporting is inaccurate or late
Analytics & Reporting Team Lead | Internal Ops | High | High | Manage Closely | Partner closely throughout; primary source for current-state pain points and validation of requirements | Reducing manual reconciliation effort without losing data accuracy
IT / Data Integration Lead | Internal Ops | Medium | High | Manage Closely | Involve early in schema and mapping design so the specification is technically buildable | Feasibility of extraction rules; ongoing maintenance burden of the new process
Vendor Relationship Manager | Internal Ops | Medium | High | Manage Closely | Co-own vendor communication; ensure specification is realistic for vendors to implement | Vendor pushback or delay if new requirements are seen as burdensome
Program / Service Team Leads (Virtual Visits, Telehealth, RPM) | Internal Ops | Medium | High | Manage Closely | Consult on dashboard data needs per service line; validate detail-schema usage | Whether their service-specific metrics are represented in the new structure
Ministry of Health Reporting Liaison | External | High | Medium | Keep Satisfied | Periodic updates on timeline and reporting continuity; no day-to-day involvement needed | Uninterrupted, accurate monthly reporting during the transition
Vendor Technical Contacts (x3) | External | Low | Medium | Keep Informed | Share the summary specification and mapping requirements once finalized; light-touch check-ins | Effort required to adjust their export process; unclear or shifting requirements
Quadrant Legend
Manage Closely | High power, high interest ( engage frequently, involve in decisions)
Keep Satisfied | High power, lower interest ( keep informed at a summary level, avoid overloading)
Keep Informed | Lower power, high interest (communicate proactively, low decision involvement)
Monitor | Low power, low interest (minimal effort, monitor for change)